## CASE STUDY 1 – PROJECT IMPLEMENTATION

The project, entitled “SMART-COAST: Sustainable Management and Resilience Tools for Coastal Areas”, aims to enhance environmental sustainability and climate resilience in coastal regions through joint planning, pilot actions, and knowledge exchange among partners from Italy, Albania, and Montenegro. The partnership consists of:

- Lead Partner (LP): University of Bari Aldo Moro (Italy)

- Project Partner 1 (PP2): Municipality of Durrës (Albania)

- Project Partner 2 (PP3): University of Montenegro (Montenegro)

- Project Partner 3 (PP4): Regional Environmental Agency of Puglia (Italy)

The total project duration is 30 months, with a total budget of €1.200.000. the project starting date set is 01/07/2024.

In December 2025, at the project midpoint, a mid-term review meeting was organized by the LP as foreseen in the F.S. 4.1 of programme Manual. The review focused on:

- Progress toward project objectives

- Financial absorption rate

- Quality of outputs

- Risk assessment and mitigation strategies

Project state of art

Overall, the project is progressing well. We completed most research and planned activities, organized 5 international workshops, and started cooperation with local stakeholders. however, the project faced some challenges in launching pilot actions and in procurement procedures, which caused delays.

At month 15, we achieved approximately 65% of planned activities, but financial expenditure is lower than expected. The lowest spending rate is registered by PP2 and PP3, mainly due to delayed pilot investments.

Critical Issues

Issue 1 – Delay in Pilot Action

The Albanian partner is 4 months late in starting a coastal monitoring pilot due to procurement delays.

The montengrin partner had delays for installation of monitoring equipment, due to supplier delays

Issue 2 – Financial Underperformance

Only 38% of the budget has been spent instead of the planned 50%.

Issue 3 – Weak Communication Strategy

Low visibility and weak dissemination impact. website traffic is low, and social media engagement is weak

TASKS

Considering that the Programme objective is to reach a financial target by December 2026 of  70% of the committed budget, you are required to:

- List the steps to be done to organize the MTR meeting and the role assigned to each partner

- Draft at least 5 mitigation measures to be undertaken by the LP to ensure project objectives achievement

- List concrete actions to do by the partnership to avoid the decommitment target by the end of December 2026 (ie. Action, responsible, deadline