CASE STUDY 2 – PROJECT ELIGIBILITY

## The project GREEN BRIDGE – Promoting Sustainable Tourism and Environmental Protection in Coastal Areas has a total duration of 24-months and total Budget: €900,000

# 1. Partnership Structure

| Partner | Country | Main Responsibilities | Budget (€) | % |
| --- | --- | --- | --- | --- |
| LP – Municipality of Bari | Italy | Project coordination, financial management, reporting, communication | 270,000 | 30% |
| PP2 – University of Tirana (Dept. of Environmental Sciences) | Albania | Environmental studies, training modules, pilot actions | 225,000 | 25% |
| PP3 – Municipality of Budva | Montenegro | Pilot actions, local stakeholder engagement, infrastructure | 270,000 | 30% |
| PP4 – NGO Adriatic Green Network | Albania | Communication, dissemination, events, community involvement | 135,000 | 15% |
|  |  |  | 900,000 | 100% |

# Partner Applied SCO

| Partner | SCO Method |
| --- | --- |
| LP – Municipality of Bari | Real staff + flat rates |
| PP2 – University of Tirana | 20% flat rate staff on other direct costs |
| PP3 – Municipality of Budva | 40% flat rate for all other costs on staff |
| PP4 – Adriatic Green Network | Real costs + flat rates |

You are part of the financial control team of the project. During a first-level control, several financial inconsistencies and eligibility problems were detected.

## LP – Municipality of Bari

| Budget Line | Declared (€) |
| --- | --- |
| Staff costs | 70,000 |
| Office & admin (15%) | 12,000 |
| Travel & accommodation (15%) | 13,000 |
| External expertise | 80,000 |
| Equipment | 45,000 |
| Infrastructure | 28,600 |
| LS preparation | 10.135 |
| LS closure | 5,865 |
| 2% FR controller costs | 5,400 |
| TOTAL | 270,000 |

## PP2 – University of Tirana

| Budget Line | Declared (€) |
| --- | --- |
| Staff (20%) | 45,000 |
| Office & admin (15%) | 6,750 |
| Travel & accommodation (15%) | 6,750 |
| External expertise | 60,000 |
| Equipment | 45,000 |
| Infrastructure | 61,500 |
| TOTAL | 225,000 |

## PP3 – Municipality of Budva

| Budget Line | Declared (€) |
| --- | --- |
| Staff | 150,000 |
| Office & admin | 15,000 |
| Travel & accommodation | 15,000 |
| Other costs | 90,000 |
| TOTAL | 270,000 |

## PP4 – Adriatic Green Network

| Budget Line | Declared (€) |
| --- | --- |
| Staff | 5,000 |
| Office & admin (15%) | 750 |
| Travel & accommodation (15%) | 600 |
| External expertise | 92,500 |
| Equipment | 36,500 |
| LS preparation | 1,595 |
| TOTAL | 135,000 |

TASKS

- Identify all errors in the declared amount by each PP

- Explain why they are incorrect

- Propose the correct solution