## CASE STUDY 4 – PROJECT REPORTING

The project “SMART-COAST: Sustainable Management and Resilience Tools for Coastal Areas”, aims to enhance environmental sustainability and climate resilience in coastal regions through joint planning, pilot actions, and knowledge exchange among partners from Italy, Albania, and Montenegro. The total project duration is 30 months, with a total budget of € 900.000. The project starting date is 01/07/2024. The partnership consists of:

| Partner | Budget (€) | % |
| --- | --- | --- |
| LP – University of Bari | 270,000 | 30% |
| PP2 – Municipality of Durres | 225,000 | 25% |
| PP3 – University of Montenegro | 270,000 | 30% |
| PP4 – Regional Environmental Agency of Puglia | 135,000 | 15% |
| TOTAL | 900,000 | 100% |

Workplan

WP1 Coastal Risk Assessment and Vulnerability Mapping: comprehensive assessment of coastal risks, including erosion, flooding, sea-level rise, and extreme weather events. Develop high-resolution vulnerability maps using GIS tools and climate projections.

- Data collection (historical climate data, shoreline changes, bathymetry, land use).

- Risk modeling and scenario analysis.

- Identification of critical infrastructure and vulnerable communities.

- Production of digital vulnerability maps and technical report.

WP2 Development of a Digital Decision-Support Tool (SMART-COAST Platform): Design and implement a digital tool to support local authorities in sustainable coastal planning and resilience strategies.

- Definition of system requirements with stakeholders.

- Development of a web-based platform integrating environmental, socio-economic, and risk indicators.

- Integration of early-warning and monitoring functionalities.

- User testing and validation workshops.

WP3 Pilot Actions for Nature-Based Solutions (NbS): Implement pilot interventions aimed at enhancing coastal resilience through nature-based solutions.

- Selection of pilot sites.

- Design and implementation of NbS measures (e.g., dune restoration, wetland rehabilitation, living shorelines).

- Environmental impact monitoring.

- Cost-benefit analysis of implemented solutions.

WP4 Capacity Building, Stakeholder Engagement and Dissemination: Strengthen institutional and community capacity for sustainable coastal management and promote knowledge transfer.

- Organization of stakeholder workshops and training sessions.

- Development of training materials and toolkits.

- Communication campaign (website, newsletters, social media).

- Final international conference.

## *********************************************

## At the third reporting period (01/07-31/12/2025), the project is in a good implementation status, and 4 Rs are going to be submitted, but the following issues occur:

- PP2 submits R1 of 25.000,00 € to its National Controller on 27/09/2025 using BL staff FR 20%, external expertise, and detailing the capacity building performed with the related evidences;

- PP3 submits R3 of 190.000,00 € to its National Controller on 30/06/2025 using BL staff real, equipment, external expertise, and detailing the coastal monitoring pilot procurement carried out, but not providing any supporting document;

- PP4 submits R2 of 35.000,00 € to the National Controller on 30/07/2025 using BL staff real, 40% other costs, and detailing the environmental study carried out, not enclosing any annex

- LP submits R3 of 70.000,00 € to the National Controller on 07/09/2025, using BL staff real, external expertise for the organization of 2 workshops, but the workshops were not described in the related activity section since the workshops minutes are uploaded

At 10/10/2025 the LP submits the PR3 to the JS/MA with the following certificates:

- LP – R3

- PP3- R3

- PP4 – R2

In the PR description, the LP describes all activities implemented in the reporting period and declares the achievement of 1 output (1.1 Integrated coastal resilience decision support system), attaching the following evidences: capacity building toolkit; 2 workshop minutes; the target group section as well as communication objectives are not filled in, considering PR an ongoing process not completed yet.

TASKS

Partner reporting (Rs)

- List the errors incurred by each Partner in its reporting procedure

- List the right audit trail to be provided in each partner report (R)

Project reporting (PRs)

- Is the PR3 ready to be approved by the JS/MA? If not, list the right audit trail to be provided by the LP in the project report (PR)

- Summarize any error detected in the reporting procedure