## CASE STUDY 5 – PROJECT CHANGES

The project, entitled “SMART-COAST: Sustainable Management and Resilience Tools for Coastal Areas”, aims to enhance environmental sustainability and climate resilience in coastal regions through joint planning, pilot actions, and knowledge exchange among partners from Italy, Albania, and Montenegro. The total project duration is 30 months, with a total budget of € 900.000. the project starting date is 01/07/2024.

## The project involves four partners:

| ## Partner | ## Budget (€) | ## % |
| --- | --- | --- |
| ## LP – University of Bari | ## 270,000 | ## 30% |
| ## PP2 – Albanian Ministry of Economy and Innovation | ## 225,000 | ## 25% |
| ## PP3 – University of Montenegro | ## 270,000 | ## 30% |
| ## PP4 – Regional Environmental Agency of Puglia | ## 135,000 | ## 15% |
| ## TOTAL | ## 900,000 | ## 100% |

During the project implementation the following changes raise:

- In the Month 3, PP2 gets an universal succession due to government changes

- In the month 5, PP4 asks for a budget change asking to shift 12.000 € from WP1 to WP2

- In the month 8, PP3 withdraws the project to the internal administrative constraints, even if it implemented activities for 70.000 €

- In the month 12, the LP needs to postpone some actions from reporting period 2 to reporting period 3

- In the month 30, the LP asks for a 6 months project extension, due to missing deliverables achievement

TASKS

- List the procedure to follow in each case, detailing When/What

- List the Jems procedure to follow in each case, detailing When/What

- Summarize the correct  timetable to be ensured by the LP for all requested changes, in compliance with the programme rules